name: Rushly MVP Roadmap overview: Establish a code-first, HLK-governed operating model and phased delivery roadmap for the Rushly MVP in use-case-2, using use-case-1 as the delivery skeleton and openclaw-akos as the stronger governance standard. The plan freezes Rushly as the canonical product scope, defers the broader brand command-center concept, and defines the repo, documentation, compliance, product, and verification structure needed to run this use case like the others. todos:

- id: p0-governance-bootstrap content: "Create the Rushly repo governance baseline: root docs, HLK compliance assets, master SOP, rule pack, planning mirror, and requirement taxonomy." status: pending

- id: p1-architecture-freeze content: Define and freeze the code-first monorepo architecture, platform contracts, CI/CD, security model, and provider decisions for storage, streaming, queueing, and vector search. status: pending

- id: p2-media-pipeline content: Implement the asynchronous media ingestion and AI processing backbone with provenance, retries, cost controls, and tenant-safe storage. status: pending

- id: p3-mvp-surface content: Ship the Rush Library, semantic search, dashboard, and six-column Kanban as the demonstrable Rushly MVP operating surface. status: pending

- id: p4-collaboration content: Add briefs, scene mapping, assignments, feedback, notifications, and exportable production handoff flows. status: pending

- id: p5-p6-differentiators-launch content: Deliver the AI differentiators, lightweight editor, billing, launch hardening, UAT evidence, and deferred-expansion boundary control. status: pending isProject: false

# Rushly Use Case 2 Operating Plan

Document owner: Holistika Admin / PMO with Websitz Product Owner
Version: 0.2
Date: 2026-04-08
Status: Review
Program mapping: Websitz > Use Case 2 > Rushly MVP
Canonical plan: Cursor-managed canonical plan for this initiative
Workspace mirror: docs/wip/planning/rushly-mvp/master-roadmap.md to be created in Phase 0

## Executive Summary

Rushly should be managed as a code-first SaaS program with HLK governance from day one, not as an unstructured build request and not as a merged "everything" e-commerce agent platform. The canonical product scope is the video-production SaaS defined in docs/references/meetings/Use case 2/Rushly_Cahier_des_charges_v2.docx.md, while the broader brand command-center concept raised in the meeting notes is explicitly deferred as a follow-on program.

## Mission

Build a SaaS for e-commerce brands and video editors that ingests raw media, processes it asynchronously, turns it into a searchable Rush Library, and supports the production workflow from import to brief to review, while also giving Holistika and Websitz a repeatable repo, PO/PM, HLK, and SSOT operating model that can be reused across later use cases.

## Accepted Decisions

- AD-01: Treat docs/references/meetings/Use case 2/Rushly_Cahier_des_charges_v2.docx.md as the canonical product scope source.

- AD-02: Treat docs/references/meetings/Use case 2/2026-04-01 15.33 - presentation projet 2.mp3.md as discovery and future-expansion evidence, not as a competing product SSOT.

- AD-03: Use a code-first repo posture, not a Bubble-first posture.

- AD-04: Reuse the delivery spine from C:/Users/Shadow/cd_shadow/websitz/use-case-1/CONTRIBUTING.md and C:/Users/Shadow/cd_shadow/websitz/use-case-1/docs/sops/SOP-HLK_WEBSITZ_SHOPIFY_APP_001-v1.md, but harden it with the precedence and checklist model from C:/Users/Shadow/cd_shadow/openclaw-akos/docs/references/hlk/compliance/PRECEDENCE.md, C:/Users/Shadow/cd_shadow/openclaw-akos/docs/DEVELOPER_CHECKLIST.md, and C:/Users/Shadow/cd_shadow/openclaw-akos/.cursor/rules/akos-planning-traceability.mdc.

- AD-05: AI outputs are assistive. Human-reviewed labels, scene mappings, and acceptance decisions override model suggestions and become canonical.

- AD-06: Multi-tenant isolation, signed media URLs, asynchronous job orchestration, RGPD deletion/export, and cost observability are mandatory from the foundation phase.

- AD-07: The broader e-commerce brand command-center concept is a deferred expansion track or separate use case after Rushly MVP stability.

- AD-08: Use one scope language across all planning artifacts: Lot 1 / MVP socle, Lot 2 / Beta, and Lot 3 / V1.1+ are partner-facing packaging terms; Phase 0 through Phase 6 remain internal execution terms.

## Constraints And Non-Goals

- The current use-case-2 workspace is not yet a git repo and currently contains discovery/reference material under docs/references/meetings/.

- Do not merge Rushly MVP and the broader command-center concept into one implementation backlog.

- Do not treat AI-generated tags, summaries, or embeddings as the primary source of business truth over human-reviewed metadata.

- Do not build a fully professional video editor in MVP. Keep the editing surface lightweight and supportive.

- Do not create parallel SSOTs for requirements, governance, or runtime contracts.

- Do not let downstream boards, mirrored docs, or future PM systems override canonical repo artifacts.

## Current-State Reality

- The current workspace contains discovery materials under docs/references/meetings/, internal estimation notes under docs/, and partner-facing coordination artifacts under gdrive/, but no production repo operating skeleton yet.

- There is currently no root README.md, CONTRIBUTING.md, CHANGELOG.md, SECURITY.md, docs/DEVELOPER_CHECKLIST.md, docs/sops/, .cursor/rules/, .github/, app skeleton, CI, or governed planning mirror for this use case.

- C:/Users/Shadow/cd_shadow/websitz/use-case-1/docs/phases/phase-5.1/gap-tracker.md shows a working pattern for SSOT status tracking separate from narrative analysis.

- C:/Users/Shadow/cd_shadow/openclaw-akos/docs/references/hlk/compliance/PRECEDENCE.md shows the stronger canonical vs mirrored vs reference-only contract that should be adopted from the start here.

## Evidence Matrix

| ID | Observation | Source | Impact |
| --- | --- | --- | --- |
| E1 | The Rushly cahier des charges defines the canonical product vision, target users, phased feature list, performance expectations, and monetization intent. | docs/references/meetings/Use case 2/Rushly_Cahier_des_charges_v2.docx.md | Establishes the authoritative product scope and the NFR baseline that later repo artifacts must not silently contradict. |
| E2 | The product-discovery conversation explicitly demands PM-led modularization, explicit estimation, and avoidance of vague generalized-AI promises. | docs/references/meetings/Use case 2/2026-04-01 15.33 - presentation projet 2.mp3.md | Justifies the lot/phase split, human-over-AI posture, and the need for explicit scope control. |
| E3 | The earlier Websitz use case already works with a master SOP, contributor guide, and phase artifact pattern. | C:/Users/Shadow/cd_shadow/websitz/use-case-1/CONTRIBUTING.md, C:/Users/Shadow/cd_shadow/websitz/use-case-1/docs/sops/SOP-HLK_WEBSITZ_SHOPIFY_APP_001-v1.md | Confirms the delivery spine to reuse for repo operations, reporting, UAT, and partner-facing execution. |
| E4 | The flagship workspace formalizes precedence, governed verification, and split Cursor rule responsibilities. | C:/Users/Shadow/cd_shadow/openclaw-akos/docs/references/hlk/compliance/PRECEDENCE.md, C:/Users/Shadow/cd_shadow/openclaw-akos/docs/DEVELOPER_CHECKLIST.md, C:/Users/Shadow/cd_shadow/openclaw-akos/.cursor/rules/akos-planning-traceability.mdc | Requires an explicit verification contract, named HLK validation step, and rule-pack shape rather than a generic promise to add them later. |
| E5 | The current workspace has partner and internal planning artifacts, but no production repo-operating assets at the root yet. | Workspace state under docs/ and gdrive/ | Makes Phase 0 a true governance bootstrap and not just a paperwork enrichment pass. |

## Product And Operating Intent

- The core user outcome is faster discovery and reuse of useful rushes, not flashy AI for its own sake.

- The core operator outcome is an auditable workflow from import to processing to library to brief to delivery.

- The UX posture should borrow clarity from Notion, Linear, and Loom, as also hinted in the cahier des charges, rather than imitate bloated editing suites.

- The DX posture should be monorepo-first, shared-schema-first, deterministic-script-first, and report-driven.

- The DI posture should be one contract authority per domain: one requirements authority, one process authority, one schema authority, one checklist authority.

- The DAMA posture should explicitly track provenance, freshness, human override, retention, deletion, and downstream derived artifacts for uploads, clips, descriptions, embeddings, and analytics.

- The SOC posture should assume workspace-level tenant isolation, least-privilege access, signed URLs, secure secrets management, and auditability.

## Stakeholders And Sign-Off

- Holistika Admin / PMO approves scope freeze, governance baselines, and phase GO or NO-GO outcomes.

- Websitz Product Owner validates priorities, UX acceptance, beta utility, and commercialization readiness.

- CTO / Tech Lead approves architecture, CI/CD, security model, and technical exit criteria.

- Data / AI owner approves model usage, evaluation quality, provenance rules, and cost posture.

- Compliance / Security owner approves retention, deletion, export, and tenant-isolation rules.

## Success Metrics

| ID | Metric | Target | Primary gate |
| --- | --- | --- | --- |
| SM1 | Governance bootstrap completeness | 100% of Phase 0 root governance assets created and linked | Phase 0 exit |
| SM2 | Requirement traceability coverage | 100% of in-scope capabilities mapped to REQ IDs, lots, and phases | Phase 0 exit |
| SM3 | Representative media processing latency | <= 60 seconds target for a 2-minute validation sample under the default pipeline profile | Lot 2 / Beta readiness |
| SM4 | Rush Library initial load | <= 2 seconds on the agreed validation dataset | Lot 1 / MVP socle sign-off |
| SM5 | Semantic search response time | <= 500 ms median on the agreed validation dataset | Lot 1 / MVP socle sign-off |
| SM6 | Preview playback start time | < 1 second median on the chosen streaming/preview path | Lot 1 / MVP socle sign-off |
| SM7 | UAT severity posture | 0 unresolved severity-1 blockers and 100% pass on critical UAT scenarios | each lot sign-off |
| SM8 | Security isolation posture | 0 unresolved cross-tenant or signed-URL severity-1 issues at lot exit | each lot sign-off |
| SM9 | Cost observability | Default analyzed-video cost stays inside the 0.02 EUR to 0.10 EUR target band, or approved variance is documented | Phase 2 exit |

## Schedule Realism

- A 3-month window can fit a first cadenced tranche, but not the full Lot 1 / MVP socle through Lot 3 / V1.1+ program as a single promise.

- Production scheduling must be frozen only after Phase 0 scope/bootstrap closure and Phase 1 architecture decisions D4 through D8.

- Partner-facing planning should treat calendar as tranche-based, not as a single all-features launch date.

## Terminology Contract

- Phase means the internal execution sequence in this canonical plan.

- Lot 1 / MVP socle means the first partner-facing, sellable core scope.

- Lot 2 / Beta means the collaborative and validation-oriented scope after the MVP socle.

- Lot 3 / V1.1+ means the controlled extension layer after the Beta scope.

- Lancement is a readiness milestone, not a backlog category.

### Lot To Phase Mapping

- Lot 1 / MVP socle maps primarily to Phase 0 through Phase 3.

- Lot 2 / Beta maps primarily to Phase 4 and the beta-relevant parts of Phase 5, plus subscriptions and readiness items from Phase 6.

- Lot 3 / V1.1+ maps to the remaining differentiators in Phase 5 and Phase 6, plus the explicitly deferred follow-ups below.

## Product Coverage Snapshot

Against the normalized 19-item backlog used in the shared product brief, this canonical plan currently:

- fully covers 15 / 19 items

- intentionally defers 4 / 19 items to Lot 3 / V1.1+ follow-up scope

## Requirement ID Convention

### Prefix Contract

| Prefix | Domain | Example capabilities |
| --- | --- | --- |
| GOV- | Governance and repo operations | root docs, rules, checklists, SOP structure |
| NF- | Non-functional and compliance | performance, RGPD, security, observability |
| WS- | Workspaces and tenancy | workspaces, projects, tenant boundaries |
| IM- | Imports and intake | direct import, Drive import, UGC link |
| MP- | Media processing | segmentation, classification, thumbnails, provenance |
| RL- | Rush Library | library views, preview, filters |
| SR- | Search and retrieval | exact and semantic search |
| DB- | Dashboard and overview | activity view, metrics, summaries |
| KP- | Production tracking | Kanban workflow |
| BR- | Briefing | scene-by-scene briefs |
| TM- | Team collaboration | roles, invites, assignments |
| FB- | Feedback | timecoded feedback flows |
| AI- | Assisted intelligence | script suggestions, competitor intelligence |
| ST- | Script templates | reusable script models |
| AN- | Analytics and reuse insights | reuse stats |
| DD- | Deduplication | duplicate detection |
| ED- | Editor and export | timeline-lite assembly and export |
| BL- | Billing and launch operations | plans, quotas, subscriptions |

### Capability Traceability Matrix

| REQ ID | Capability | Lot | Primary phase | Status |
| --- | --- | --- | --- | --- |
| WS-01 | Multi-projects / Workspaces | Lot 1 / MVP socle | Phase 1 and Phase 3 | In scope |
| IM-01 | Direct media import | Lot 1 / MVP socle | Phase 2 | In scope |
| IM-02 | Google Drive import | Lot 2 / Beta | Phase 4 | In scope |
| IM-03 | UGC creator link | Lot 3 / V1.1+ | Deferred follow-up | Deferred |
| MP-01 | AI segmentation and classification | Lot 1 / MVP socle | Phase 2 | In scope |
| RL-01 | Rush Library | Lot 1 / MVP socle | Phase 3 | In scope |
| SR-01 | Semantic search | Lot 1 / MVP socle | Phase 3 | In scope |
| DB-01 | Dashboard / activity view | Lot 1 / MVP socle | Phase 3 | In scope |
| KP-01 | Kanban Production | Lot 1 / MVP socle | Phase 3 | In scope |
| BR-01 | Brief scene by scene | Lot 2 / Beta | Phase 4 | In scope |
| TM-01 | Team collaboration | Lot 2 / Beta | Phase 4 | In scope |
| FB-01 | Frame-by-frame feedback | Lot 2 / Beta | Phase 4 | In scope |
| AI-01 | Script-to-rush suggestions | Lot 2 / Beta | Phase 5 | In scope |
| AI-02 | Competitor clone | Lot 3 / V1.1+ | Phase 5 | In scope |
| BL-01 | Plans and subscriptions | Lot 2 / Beta | Phase 6 | In scope |
| ED-01 | Lightweight editor + export | Lot 3 / V1.1+ | Phase 6 | In scope |
| ST-01 | Script templates | Lot 3 / V1.1+ | Deferred follow-up | Deferred |
| AN-01 | Reuse stats | Lot 3 / V1.1+ | Deferred follow-up | Deferred |
| DD-01 | Duplicate detection | Lot 3 / V1.1+ | Deferred follow-up | Deferred |

### Coverage Notes

- The original cahier des charges item Import flexible is covered in split form: direct import and Google Drive import are in scope; the UGC creator link is explicitly deferred.

- The original cahier des charges item Script -> montage IA is covered across two phases rather than one block: script-to-rush intelligence in Phase 5, then lightweight assembly and export in Phase 6.

- Every implementation PR must reference at least one REQ ID from the table above and one phase action ID from the relevant execution section.

## Open Questions And Decision Log

| ID | Question | Options | Current decision | Owner / gate |
| --- | --- | --- | --- | --- |
| D1 | Canonical product scope | Rushly MVP / broader command-center / combined scope | Rushly MVP | Holistika Admin + Websitz Product Owner |
| D2 | Broader agentic brand-workspace concept | merge now / later phase / separate use case | Later phase or separate use case | Holistika Admin + Websitz Product Owner |
| D3 | Delivery posture | Bubble-first / code-first / hybrid | Code-first | Holistika Admin + CTO |
| D4 | Storage provider for canonical media assets | Cloudflare R2 / AWS S3 | TBD in Phase 1 architecture freeze | CTO + PMO |
| D5 | Streaming and preview provider | Mux / api.video | TBD in Phase 1 architecture freeze | CTO + PMO |
| D6 | Queue and orchestration layer | Inngest / Trigger.dev / BullMQ-Redis | TBD in Phase 1 architecture freeze | CTO + PMO |
| D7 | Import sequencing | direct upload only / direct upload plus Google Drive / all flexible imports | Direct upload in Lot 1, Google Drive in Lot 2, UGC link in Lot 3 | Product Owner + CTO |
| D8 | Launch language strategy | French-only / bilingual / multilingual | TBD before Beta sign-off | Product Owner + PMO |

## Meta-Process And SOP Ownership

- docs/sops/SOP-HLK_WEBSITZ_RUSHLY_001-v1.md is the canonical delivery SOP for this use-case repository once Phase 0 is complete.

- docs/references/hlk/compliance/SOP-META_PROCESS_MGMT_001.md is the governing meta-process template and local governance reference for how the Rushly SOP, process rows, and reporting artifacts must be structured.

- If the use-case SOP and the meta-SOP ever diverge on process structure, the meta-SOP governs the template and the use-case SOP governs initiative-specific execution details.

- Phase 0 must define stable process_list.csv rows for the Rushly initiative so the project, workstreams, processes, and tasks are traceable in the same governance model as the flagship workspaces.

## Asset Classification

### Canonical Assets

- docs/references/baseline_requirements/product-requirements.md

- docs/references/baseline_requirements/technical-specification.md

- docs/references/baseline_requirements/competitive-analysis.md

- docs/references/baseline_requirements/project-timeline.md

- docs/sops/SOP-HLK_WEBSITZ_RUSHLY_001-v1.md

- docs/references/hlk/compliance/SOP-META_PROCESS_MGMT_001.md

- docs/references/hlk/compliance/PRECEDENCE.md

- docs/references/hlk/compliance/baseline_organisation.csv

- docs/references/hlk/compliance/process_list.csv

- docs/references/hlk/compliance/access_levels.md

- docs/references/hlk/compliance/confidence_levels.md

- docs/references/hlk/compliance/source_taxonomy.md

- docs/DEVELOPER_CHECKLIST.md

- CONTRIBUTING.md

- .cursor/rules/

### Mirrored Or Derived Assets

- docs/wip/planning/rushly-mvp/master-roadmap.md as the workspace mirror of the canonical Cursor plan

- external PM boards, milestone trackers, and commercial follow-up trackers

- generated schema diagrams, migration artifacts, and API clients

- deployed environment templates and observability dashboards

- downstream Drive or knowledge-base mirrors

### Reference-Only Assets

- docs/references/meetings/Use case 2/

- C:/Users/Shadow/cd_shadow/websitz/use-case-1/

- C:/Users/Shadow/cd_shadow/openclaw-akos/

- C:/Users/Shadow/cd_shadow/root_cd/kirbe/

- the other inspiration repos cited by the user

### Drift Handling Rule

Canonical wins. If meeting notes, PM systems, workspace mirrors, or runtime artifacts contradict the canonical repo artifacts, stop execution, resolve the contradiction in the decision log, then resync the mirror.

## Phase 0 Repo Operating Contract

| Artifact | Path | Contract |
| --- | --- | --- |
| Root contribution contract | CONTRIBUTING.md | Defines branch strategy, REQ-ID usage, PR review discipline, and merge policy. |
| Root orientation docs | README.md, CHANGELOG.md, SECURITY.md | Provide repo entry, release notes, and security posture. |
| Delivery SOP | docs/sops/SOP-HLK_WEBSITZ_RUSHLY_001-v1.md | Canonical delivery SSOT for this repository. |
| Meta-process mirror | docs/references/hlk/compliance/SOP-META_PROCESS_MGMT_001.md | Governs process structure, process_list.csv, and SOP formatting. |
| Developer verification authority | docs/DEVELOPER_CHECKLIST.md | Single verification matrix authority for pre-merge and release gates. |
| UAT layout | docs/sops/uat/dev-uat/, docs/sops/uat/user-uat/ | Separate technical and user-facing UAT artifacts. |
| Phase reporting layout | docs/phases/phase-0/ through docs/phases/phase-6/ | Phase plans, completion reports, and remediation evidence. |
| Gap remediation tracker | docs/phases/phase-0/gap-tracker.md or later phase equivalent | Required when audits or reviews generate multi-wave remediation work. |
| Rule pack | .cursor/rules/rushly-governance.mdc, .cursor/rules/rushly-planning-traceability.mdc, .cursor/rules/rushly-docs-sync.mdc | Split rules for governance, planning traceability, and doc-sync rather than one thin all-purpose rule. |
| GitHub collaboration defaults | .github/workflows/ci.yml, .github/PULL_REQUEST_TEMPLATE.md, .github/CODEOWNERS, .github/dependabot.yml | Required for CI, review ownership, PR hygiene, and dependency policy. |
| Planning mirror | docs/wip/planning/rushly-mvp/master-roadmap.md | Workspace mirror of this canonical Cursor-managed plan. |

### Cursor Rule Contract

- .cursor/rules/rushly-governance.mdc should be alwaysApply and govern SSOT, DI, SOC, verification expectations, and phase discipline.

- .cursor/rules/rushly-planning-traceability.mdc should govern docs/wip/, plan mirrors, reports, asset classification, and planning traceability requirements.

- .cursor/rules/rushly-docs-sync.mdc should govern documentation updates triggered by config, model, script, test, or rule changes.

### Review Discipline

- Feature work targets develop; main is reserved for reviewed, release-ready merges.

- Every runtime or schema PR requires at least one technical reviewer.

- Every user-facing scope or UX change requires Product Owner review.

- Every change to canonical HLK assets or scope/billing policy requires Admin or PMO approval.

- release:gate must pass before merge to main.

## Recommended Workspace Structure

use-case-2/

README.md

CONTRIBUTING.md

CHANGELOG.md

SECURITY.md

.cursor/rules/

.github/workflows/

.github/PULL_REQUEST_TEMPLATE.md

.github/CODEOWNERS

.github/dependabot.yml

apps/web/

apps/api/

apps/worker/

packages/domain/

packages/ui/

packages/config/

packages/testing/

infra/

scripts/

tests/

docs/ARCHITECTURE.md

docs/USER_GUIDE.md

docs/DEVELOPER_CHECKLIST.md

docs/sops/

docs/sops/uat/dev-uat/

docs/sops/uat/user-uat/

docs/phases/phase-0/ through phase-6/

docs/references/baseline_requirements/

docs/references/hlk/compliance/

docs/wip/planning/rushly-mvp/reports/

## Phase Structure

flowchart LR

phase0["P0 Governance And Scope Freeze"] --> phase1["P1 Platform Architecture And Monorepo Foundation"]

phase1 --> phase2["P2 Media Ingestion And AI Processing Backbone"]

phase2 --> phase3["P3 Rush Library Search Dashboard And Kanban MVP"]

phase3 --> phase4["P4 Briefs Collaboration And Review Flows"]

phase4 --> phase5["P5 Script Assist And Competitor Clone"]

phase5 --> phase6["P6 Lightweight Editor Billing And Launch Hardening"]

phase3 --> expansion["Deferred Expansion Brand Command Center"]

## Per-Phase Work Items

### Phase 0: Governance, Scope Freeze, And Repo Bootstrap

- Goal: Turn the current folder into a governed repo and freeze Rushly MVP as the canonical program.

- Sprint profile: High leverage, low runtime risk, medium coordination risk.

- Primary files: README.md, CONTRIBUTING.md, CHANGELOG.md, SECURITY.md, docs/DEVELOPER_CHECKLIST.md, docs/references/baseline_requirements/, docs/references/hlk/compliance/, docs/sops/, docs/sops/uat/, docs/wip/planning/rushly-mvp/, .cursor/rules/, .github/.

- Design decision: Use the flagship governance model from openclaw-akos while keeping the delivery language compatible with Websitz use-case conventions.

- Action IDs: P0.GOV.1 initialize git and root repo docs; P0.GOV.2 create the HLK compliance baseline and precedence contract; P0.GOV.3 author PRD, tech spec, timeline, and competitive baseline from the meeting sources; P0.GOV.4 author the master Rushly SOP, meta-SOP mirror, and phase folders; P0.GOV.5 create the developer checklist and split Cursor rule pack; P0.GOV.6 create the in-repo planning mirror; P0.GOV.7 freeze requirement prefixes, capability mapping, and commit traceability; P0.GOV.8 define GitHub workflow defaults, PR template, CODEOWNERS, and review discipline; P0.GOV.9 define the named validation scripts and release-gate contract; P0.GOV.10 define UAT layout and gap-tracker conventions.

- Acceptance criteria: Repo exists as a governed workspace with canonical docs, split rule pack, branch strategy, requirement ID scheme, named validation scripts, GitHub collaboration defaults, and explicit deferred scope for the broader command-center idea.

- Exit criteria: The team can begin execution with one agreed scope and one agreed governance stack.

- Rollback criteria: If scope contradictions remain unresolved, pause before any runtime scaffold and revise only the canonical docs.

- Commit target: docs(rushly): establish governance SSOT and phase-0 baseline

### Phase 1: Platform Architecture And Monorepo Foundation

- Goal: Freeze the technical architecture and create the code-first platform substrate.

- Sprint profile: Medium-high technical risk and mandatory before feature work.

- Primary files: root workspace config, apps/web/, apps/api/, apps/worker/, packages/domain/, packages/ui/, packages/config/, docs/ARCHITECTURE.md, .env.example, CI files, and bootstrap scripts.

- Design decision: Prefer a TypeScript monorepo with separate web, API, and worker surfaces plus shared domain contracts.

- Action IDs: P1.ARCH.1 choose framework stack and package manager; P1.ARCH.2 model auth, RBAC, tenant isolation, and workspace boundaries; P1.ARCH.3 choose storage, streaming, queue, and vector providers; P1.ARCH.4 implement CI/CD, typecheck, lint, and test scaffolding; P1.ARCH.5 implement logging, health checks, and cost telemetry scaffolding; P1.ARCH.6 seed repeatable demo data and sample media.

- Acceptance criteria: Authenticated shell deploys, workspace and project creation work, signed upload starts, one background job executes, and architecture decisions D4 through D8 are frozen or explicitly deferred.

- Exit criteria: Architecture is stable enough to build the media pipeline without replatforming.

- Rollback criteria: If the chosen stack becomes too complex or brittle, simplify the web/API/worker split before media work proceeds.

- Commit target: feat(platform): scaffold Rushly monorepo and architecture baseline

### Phase 2: Media Ingestion And AI Processing Backbone

- Goal: Make upload to processed-rush deterministic, observable, and safe.

- Sprint profile: Highest technical and cost risk in the roadmap.

- Primary files: upload modules, worker jobs, DB schema and migrations, media domain models, import UI surfaces, and architecture docs.

- Design decision: Use an asynchronous state-machine pipeline with explicit retry rules and operator-visible failure states.

- Action IDs: P2.MEDIA.1 implement file upload and storage binding; P2.MEDIA.2 implement FFmpeg segmentation and thumbnails; P2.MEDIA.3 implement transcription, visual analysis, classification, and embeddings; P2.MEDIA.4 persist provenance, status, retries, and reprocessing controls; P2.MEDIA.5 add cost tracking and quota guardrails.

- Acceptance criteria: A representative raw video becomes a set of searchable rush clips with thumbnails, tags, descriptions, provenance metadata, and auditable processing state.

- Exit criteria: The pipeline handles partner sample media with acceptable latency and no cross-tenant leakage.

- Rollback criteria: Disable unstable enrichment stages independently while preserving raw upload and basic processing.

- Commit target: feat(media): deliver Rushly ingestion and AI processing pipeline

### Phase 3: Rush Library, Search, Dashboard, And Kanban MVP

- Goal: Ship the Lot 1 / MVP socle value the partner can show and sell.

- Sprint profile: High UX value and medium technical risk.

- Primary files: library, search, dashboard, and kanban app surfaces plus shared UI and domain packages.

- Design decision: The Library and Kanban are the daily operating surfaces; the dashboard supports orientation and action rather than vanity reporting.

- Action IDs: P3.MVP.1 build the Rush Library grid and list views with preview and filters; P3.MVP.2 build semantic and exact search with ranking fallback; P3.MVP.3 build workspace and project overview surfaces; P3.MVP.4 build the 6-column Kanban with assignment and deadlines; P3.MVP.5 add robust loading, empty, and processing-state UX.

- Acceptance criteria: A user can move from processed media to searchable library to active production workflow without leaving the platform.

- Exit criteria: Websitz can demonstrate a coherent Rushly MVP journey to prospects and pilot users.

- Rollback criteria: If advanced Kanban behavior threatens schedule, ship a simpler status board before filters and automations.

- Commit target: feat(mvp): ship library search dashboard and kanban workflow

### Phase 4: Briefs, Collaboration, And Review Flows

- Goal: Turn the media library into a production collaboration system.

- Sprint profile: Medium risk and high retention value.

- Primary files: brief, scene, feedback, PDF export, assignment, and notification modules.

- Design decision: Human workflow first and AI suggestion second.

- Action IDs: P4.BRIEF.1 implement the brief and scene data model; P4.BRIEF.2 implement rush linking and AI suggestion per scene; P4.BRIEF.3 implement roles, invitations, and assignments; P4.BRIEF.4 implement timecode comments and PDF export; P4.BRIEF.5 implement notifications and activity history; P4.BRIEF.6 implement Google Drive import into the existing media intake pipeline for collaborative production use.

- Acceptance criteria: A marketer can create a brief, map scenes to rushes, assign work, export the brief, keep review comments in the app, and ingest Drive-hosted media into the same project-bound pipeline.

- Exit criteria: The partner can run the core production workflow without external Notion or Drive sprawl.

- Rollback criteria: If timing is tight, keep advanced notifications and permission variants simple while preserving brief, scene, and feedback core flows.

- Commit target: feat(collab): add briefs scene mapping and feedback workflow

### Phase 5: Differentiators, Script Assist, And Competitor Clone

- Goal: Ship the intelligence layer that spans late-Beta assistance and the first Lot 3 / V1.1+ differentiators.

- Sprint profile: High product value and high model-quality risk.

- Primary files: script analysis services, competitor intake modules, matching and ranking logic, suggestion UI, and evaluation docs.

- Design decision: Every AI suggestion remains editable and traceable; do not promise fully autonomous creative decisions.

- Action IDs: P5.AI.1 implement script parsing and rush suggestion; P5.AI.2 implement competitor video intake and scene-structure analysis; P5.AI.3 implement rush matching against competitor structure; P5.AI.4 implement prefilled brief or sequence proposal UX; P5.AI.5 implement quality evaluation and failure taxonomy.

- Acceptance criteria: The user can supply a script or competitor reference and receive a useful first-pass mapping that accelerates work, with script assistance ready for Lot 2 / Beta and competitor intelligence ready for Lot 3 / V1.1+.

- Exit criteria: Phase 5 outputs are validated against real user acceptance rather than model confidence alone, and the Lot 2 versus Lot 3 split remains explicit in release planning.

- Rollback criteria: If full clone quality is weak, reduce the feature to scene analysis plus rush suggestion instead of auto-building a complete brief.

- Commit target: feat(ai): deliver script assist and competitor intelligence layer

### Phase 6: Lightweight Editor, Billing, Launch Hardening, And Go-To-Market Readiness

- Goal: Reach a launchable posture for Beta monetization and the first controlled Lot 3 / V1.1+ release without bloating the product.

- Sprint profile: Medium-high integration risk.

- Primary files: editor module, render and export services, billing modules, launch docs, user guide, security docs, and phase reports.

- Design decision: Keep the editor lightweight and fast. It should produce a workable creative draft, not compete with full NLE suites.

- Action IDs: P6.LAUNCH.1 implement timeline reorder, trim, and preview; P6.LAUNCH.2 implement subtitles, TTS or voiceover, and MP4 or SRT export; P6.LAUNCH.3 implement Stripe plans, trials, and quotas; P6.LAUNCH.4 implement monitoring, alerts, backup, restore, and incident runbooks; P6.LAUNCH.5 finalize UAT, onboarding, and launch evidence.

- Acceptance criteria: Beta users can pay, produce, export, and receive supportable service levels, while the lightweight editor remains explicitly scoped as a Lot 3 / V1.1+ differentiator rather than a full editing suite.

- Exit criteria: Launch candidate approved by the required sign-off roles.

- Rollback criteria: If editor rendering threatens stability, ship collaboration and export first and defer more advanced editing controls.

- Commit target: feat(launch): harden editor billing and launch operations

## Targeted Test Plan

- T0: Governance validation for doc links, rule coverage, phase-folder structure, and planning mirror synchronization.

- T1: Auth and tenant-isolation tests for workspace separation, signed URL expiry, role enforcement, and deletion or export flows.

- T2: Media pipeline tests for upload, segmentation, transcription, classification, embeddings, retries, failure recovery, and provenance capture.

- T3: Search and library tests for exact match, semantic ranking, filters, pagination, and human override propagation.

- T4: Kanban and brief tests for status transitions, scene mapping, feedback timecodes, notifications, and PDF export.

- T5: AI-assist evaluation tests for script suggestion relevance, competitor scene mapping quality, and safe degradation under low confidence.

- T6: Editor and export tests for reorder, trim, subtitle sync, render completion, and file-download integrity.

- T7: Billing and quota tests for plan enforcement, trial handling, storage caps, and webhook correctness.

- T8: End-to-end smoke journey for the canonical persona from workspace creation to export or briefing milestone.

## Governed Verification Matrix

- docs/DEVELOPER_CHECKLIST.md is the single verification authority for this repo once created in Phase 0.

- docs/DEVELOPER_CHECKLIST.md must cover root quality gates, runtime/API/worker smoke gates, docs-sync gates, HLK-compliance gates, UAT gates, and release-gate ownership.

- Phase 0 must define the following canonical root scripts and their CI jobs, regardless of package manager transport:

| Gate | Canonical root script | Backing script / contract | CI job |
| --- | --- | --- | --- |
| Lint | quality:lint | workspace lint contract | quality |
| Typecheck | quality:typecheck | workspace typecheck contract | quality |
| Unit tests | test:unit | unit test suite | test-unit |
| Integration tests | test:integration | integration test suite | test-integration |
| API smoke | smoke:api | API smoke contract | smoke-runtime |
| Worker smoke | smoke:worker | worker/queue smoke contract | smoke-runtime |
| Browser or E2E smoke | smoke:e2e | partner-visible journey smoke | smoke-e2e |
| Docs and links | docs:check | scripts/check-doc-links.ts and docs-sync checks | docs-sync |
| HLK validation | hlk:validate | scripts/validate-hlk.ts as the repo-equivalent of flagship HLK validation | hlk-validate |
| Unified release gate | release:gate | scripts/release-gate.ts aggregating the governed matrix | release-gate |

- docs/references/hlk/compliance/ changes must explicitly run hlk:validate and release:gate.

- .github/workflows/ci.yml must run the governed matrix on PRs to develop and on pushes to main.

- No phase plan or completion report should name a verification set narrower than the governed checklist.

## UAT Acceptance Matrix

- UAT-1: A solo brand operator can create a workspace, create a project, and import raw video.

- UAT-2: Rushly processes the upload into browsable rushes with useful tags, thumbnails, and searchability.

- UAT-3: An operator can move a production item through the six canonical Kanban statuses without confusion.

- UAT-4: A marketer can create a scene-by-scene brief, link rushes, and export or share the brief.

- UAT-5: An editor can receive and answer timecoded feedback inside the platform.

- UAT-6: The product owner judges script assistance and competitor-clone assistance as helpful accelerators rather than blockers.

- UAT-7: An admin can manage billing, quotas, workspace separation, and basic launch operations safely.

## Documentation Sync Matrix

- Product scope changes update the PRD, technical specification, project timeline, SOP, planning mirror, and current phase report.

- Runtime and architecture changes update docs/ARCHITECTURE.md, docs/USER_GUIDE.md, CONTRIBUTING.md, .cursor/rules/, and CHANGELOG.md.

- HLK governance changes update docs/references/hlk/compliance/PRECEDENCE.md, the canonical baselines in the same folder, docs/DEVELOPER_CHECKLIST.md, and any affected rules.

- UX and workflow changes update UAT docs, onboarding and demo guides, and acceptance evidence.

## Risks And Rollback

| ID | Risk | Likelihood | Impact | Mitigation | Rollback |
| --- | --- | --- | --- | --- | --- |
| R1 | Scope creep toward the broader command-center platform | High | High | Enforce AD-07, lot boundaries, and decision-log change control | Move new requests to deferred follow-up |
| R2 | Media processing cost or latency becomes unacceptable | Medium | High | Use asynchronous queues, per-stage toggles, quotas, cost telemetry, and fallback models | Keep upload and basic manual workflows while disabling expensive enrichment |
| R3 | Search quality is weak | Medium | Medium | Use hybrid keyword plus vector strategy, human override, and evaluation harness | Keep exact and faceted search usable while semantic ranking is tuned |
| R4 | The lightweight editor expands into a full NLE scope | Medium | High | Keep the non-goal explicit in every phase gate and lot boundary | Ship export and collaboration without advanced editor features |
| R5 | Governance drift emerges between docs, rules, and runtime | Medium | High | Use the precedence contract, checklist, docs-sync rule, and planning mirror discipline | Freeze execution until canonical docs are reconciled |
| R6 | Tenant or security leakage occurs | Low | Critical | Enforce least privilege, signed URLs, audit logs, deletion tests, and tenant isolation reviews | Disable the affected surface and rotate access paths before reopening |
| R7 | Calendar expectations collapse because a full multi-lot program is mistaken for one short tranche | High | High | Keep schedule realism explicit and sell or plan by tranche | Re-baseline around the current lot and defer later lots formally |

## Commit Strategy

- One phase-scoped merge target per phase once execution starts; working branches may contain multiple implementation commits, but each phase should close with one clearly attributable merge outcome and report artifact.

- Expected phase-scoped commit pattern:

- docs(rushly): establish governance SSOT and phase-0 baseline

- feat(platform): scaffold Rushly monorepo and architecture baseline

- feat(media): deliver Rushly ingestion and AI processing pipeline

- feat(mvp): ship library search dashboard and kanban workflow

- feat(collab): add briefs scene mapping and feedback workflow

- feat(ai): deliver script assist and competitor intelligence layer

- feat(launch): harden editor billing and launch operations

## Reporting Artifacts

- docs/phases/phase-0/ through docs/phases/phase-6/ each contain a phase plan and completion report.

- docs/wip/planning/rushly-mvp/reports/ mirrors execution-relevant reports when needed for workspace traceability.

- UAT plans, UAT completion notes, cost-baseline memos, AI evaluation notes, and gap-trackers are produced for the phases that introduce those concerns.

## Exit Criteria

- Rushly MVP scope is frozen, documented, and separated from the broader future expansion.

- The repo has an HLK-governed operating model with clear canonical, mirrored, and reference-only assets.

- The team can execute through explicit phases, requirement IDs, sign-off gates, and verification gates.

- The platform architecture supports secure multi-tenant media processing and later expansion without duplicate frameworks or parallel SSOTs.

- This use case can be managed the same way as the other governed programs: plan, execute, verify, report, and hand off.

## Deferred Follow-Ups

- The broader brand command-center or agentic workspace concept from the earlier meeting.

- UGC creator link.

- Script templates.

- Reuse stats.

- Duplicate detection.

- Deep cross-tool brand-management integrations beyond the Rushly core product.

- Full professional editing features, advanced motion graphics, and music tooling.

- Cross-use-case shared service extraction after Rushly MVP proves stable and governance-clean.