# Rushly - Internal effort and revenue estimate

Audience: Holistika internal only
Security level: Internal / Do not share in GDrive
Version: 0.2
Date: 2026-04-08
Basis: C:\Users\Shadow\.cursor\plans\rushly_mvp_roadmap_3cd96613.plan.md

## 1. Objective

This document translates the current Rushly roadmap into:

- internal effort estimates in hours and days

- delivery envelopes by lot

- indicative project revenue using an HLK moderate baseline

- ES / blended / FR market comparison scenarios

This is a commercial and scoping support document. It is not the partner-facing product brief.

## 2. Estimation assumptions

- 1 day = 8 hours

- Estimates are directional and suitable for feasibility and pricing discussion, not final contract locking.

- Figures assume a code-first product repo as defined in the roadmap.

- Figures include production effort, PM / PO coordination, and a reasonable QA / stabilization load.

- Figures exclude VAT, legal setup, external paid media, post-launch support retainers, and long-tail maintenance.

- Figures also exclude infra / AI usage pass-through costs unless sold as a bundled managed service.

- HLK moderate is the primary planning basis in this document.

- HLK moderate is set to 4/5 of the ES moderate estimate envelope, applying the expected productivity leverage from the HLK operating model.

- ES / blended / FR moderate scenarios are kept for market comparison only.

## 3. Commercial baseline and market comparison scenarios

| Scenario | Pricing / effort rule | Use |
| --- | --- | --- |
| HLK moderate | 80% of the ES moderate estimate envelope | Primary internal planning baseline |
| ES moderate | 450 EUR / day on the raw market envelope | Market comparison |
| FR-ES blended moderate | 550 EUR / day on the raw market envelope | Market comparison |
| FR moderate | 650 EUR / day on the raw market envelope | Market comparison |

## 4. HLK moderate delivery envelope by lot

| Lot | Scope logic | Hours | Days |
| --- | --- | --- | --- |
| Lot 1 / MVP socle | MVP visible and sellable | 793.6 | 99.2 |
| Lot 2 / Beta | Collaborative beta and monetization layer | 352.0 | 44.0 |
| Lot 3 / V1.1+ | Differentiation and controlled expansion | 358.4 | 44.8 |
| Total | Full roadmap envelope | 1504.0 | 188.0 |

## 5. What is included in each lot

### Lot 1 / MVP socle

Included:

- governance and scoping baseline needed to start cleanly

- platform foundation

- Multi-project / Workspace model

- direct media import

- AI segmentation and classification backbone

- Rush Library

- semantic search

- dashboard / activity view

- Kanban Production

- first QA / stabilization layer

### Lot 2 / Beta

Included:

- brief scene by scene

- team collaboration

- frame-by-frame feedback

- Google Drive import

- plans and subscriptions

- script-to-rush suggestion layer

- associated QA / PM overhead

### Lot 3 / V1.1+

Included:

- competitor clone flow

- lightweight editor and export

- UGC upload link

- script templates

- reuse stats

- duplicate detection

- launch-side QA / PM overhead

## 6. HLK moderate feature-level estimate

| Function | Hours | Days | Notes |
| --- | --- | --- | --- |
| Multi-projects / Workspaces | 38.4 | 4.8 | Workspace, project boundaries, base UX |
| Direct media import | 51.2 | 6.4 | Raw video and ready-rush ingestion |
| Google Drive import | 25.6 | 3.2 | OAuth and external import path |
| UGC creator link | 25.6 | 3.2 | External upload without full account path |
| AI segmentation + classification | 140.8 | 17.6 | Core AI backbone, processing states, retries |
| Rush Library | 57.6 | 7.2 | Grid / list / preview / filters |
| Semantic search | 51.2 | 6.4 | Exact + vector search behavior |
| Dashboard / activity view | 32.0 | 4.0 | Summary, activity, orientation layer |
| Kanban Production | 51.2 | 6.4 | Production pipeline and card logic |
| Brief scene by scene | 57.6 | 7.2 | Scene structure and rush linking |
| Team collaboration | 38.4 | 4.8 | Roles, invitations, assignment basics |
| Frame-by-frame feedback | 44.8 | 5.6 | Timecoded feedback flow |
| Script-to-rush suggestions | 64.0 | 8.0 | Assisted matching layer |
| Competitor clone | 76.8 | 9.6 | Import, parse, match, prefill logic |
| Script templates | 19.2 | 2.4 | Reusable templates and management |
| Reuse stats | 19.2 | 2.4 | Basic usage and reuse insights |
| Duplicate detection | 32.0 | 4.0 | Similarity / flagging logic |
| Lightweight editor + export | 102.4 | 12.8 | Timeline-lite, subtitle / export logic |
| Plans and subscriptions | 32.0 | 4.0 | Billing plans and access control |
| Product feature subtotal | 960.0 | 120.0 |  |

## 7. HLK moderate non-feature workload that must still be priced

| Workstream | Hours | Days | Notes |
| --- | --- | --- | --- |
| Governance, scoping, product baseline | 64.0 | 8.0 | Feasibility, product framing, roadmap hygiene |
| Platform foundation, architecture, CI, security base | 192.0 | 24.0 | Monorepo, auth, environments, observability base |
| QA, UAT, release stabilization | 160.0 | 20.0 | Cross-phase test, smoke, stabilization effort |
| PM / PO coordination and delivery management | 128.0 | 16.0 | Stakeholder sync, arbitration, backlog and milestone control |
| Non-feature subtotal | 544.0 | 68.0 |  |

## 8. HLK moderate total effort summary

| Category | Hours | Days |
| --- | --- | --- |
| Product features | 960.0 | 120.0 |
| Non-feature delivery load | 544.0 | 68.0 |
| Grand total | 1504.0 | 188.0 |

## 9. Commercial comparison by lot

| Lot | HLK moderate | ES moderate | FR-ES blended moderate | FR moderate |
| --- | --- | --- | --- | --- |
| Lot 1 / MVP socle | 44,640 EUR | 55,800 EUR | 68,200 EUR | 80,600 EUR |
| Lot 2 / Beta | 19,800 EUR | 24,750 EUR | 30,250 EUR | 35,750 EUR |
| Lot 3 / V1.1+ | 20,160 EUR | 25,200 EUR | 30,800 EUR | 36,400 EUR |
| Total | 84,600 EUR | 105,750 EUR | 129,250 EUR | 152,750 EUR |

### Recommended internal reading

- HLK moderate is the internal baseline to use for effort and pricing discussions.

- If we sell only Lot 1 / MVP socle, the baseline project revenue is 44.64k EUR.

- If we sell through Lot 2 / Beta, the cumulative baseline project revenue is 64.44k EUR.

- If we sell the full roadmap envelope through Lot 3 / V1.1+, the baseline project revenue is 84.6k EUR.

- ES / blended / FR columns should be read only as market comparison references.

## 10. Commercial recommendation

### Recommended sell posture

- Do not sell the whole product as a single fixed low-price block.

- Sell by lots with explicit scope boundaries.

- Keep AI-heavy differentiators outside the first commercial promise unless specifically paid for.

- Use HLK moderate as the internal baseline for effort and pricing discussions.

### Suggested commercial framing

- Lot 1 / MVP socle: first paid tranche and first validation gate

- Lot 2 / Beta: second commercial step once the product is demonstrable

- Lot 3 / V1.1+: optional extension or later roadmap sale

### Internal caution

For a project involving video processing, AI orchestration, search, collaboration, and billing, pricing below the HLK moderate baseline would compress margin too aggressively unless:

- scope is cut materially

- internal reuse is unusually high

- or part of the work is financed as strategic flagship investment

## 11. Optional quote orientation

If we want commercial safety rather than bare baseline multiplication, the quote orientation could be:

| Package | HLK moderate baseline | Safer commercial band |
| --- | --- | --- |
| Lot 1 / MVP socle | 44,640 EUR | 50,000 - 58,000 EUR |
| Lot 1 + Lot 2 | 64,440 EUR | 70,000 - 80,000 EUR |
| Full roadmap envelope | 84,600 EUR | 90,000 - 105,000 EUR |

This band assumes normal contingency for:

- AI/video uncertainty

- partner-side feedback loops

- integration clarification

- scope friction during delivery

## 12. What this estimate does not include

- recurring SaaS revenue after launch

- support retainer revenue

- infra resale margin

- separate consulting, audit, or strategy revenue outside the product build

It is advised to estimate downstream SaaS upside separately from delivery revenue.